## Report
ACC BCC Expansion Project | [13 empty] | Cody Cusey - ITS 221 - Assignment 10
Earned Value Analysis Report
Earned Value Management Template
| Prepared By: | Cody Cusey | [12 empty] | © 2012-2021 Vertex42 LLC
| Date: | 2025-03-13
[42]
| For Period: | Week 12
Summary:
The ACC BCC Expansion Project will take approximately 12 months to complete. This Earned Value Analysis Report outlines the Work Breakdown Structure, timeline for each work package, and the costs associated to complete the WBS element.
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS) | [6 empty] | Months
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | ← You can change the labels for the periods (e.g. Week 1/2/3, Jan/Feb/Mar, etc.)
1.1.1 | Evaluation & Recommendations | 5000 | 5000 | [11 empty] | ← Enter or edit values in the light-blue cells.
1.1.2 | Develop Project Charter | 35000 | 15000 | 20000
1.1.3 | Deliverable: Submit Project Charter | 5000 |  | 5000
1.1.4 | Project Sponsor Reviews Project Charter | 3000 | 2000 | 1000
1.1.5 | Project Charter Signed/Approved | 1000 |  | 1000
1.2.1 | Create Preliminary Scope Statement | 10000 |  | 10000
1.2.2 | Determine Project Team | 55000 |  | 5000 | 50000
1.2.3 | Project Team Kickoff Meeting | 10000 |  |  | 10000
1.2.4 | Develop Project Plan | 50000 |  |  | 25000 | 25000
1.2.5 | Submit Project Plan | 20000 |  |  |  | 20000
1.2.6 | Milestone: Project Plan Approval | 1000 |  |  |  | 1000
1.3.1 | Project Kickoff Meeting | 25000 |  |  |  | 25000
1.3.2 | Confirm Deliverables and Deadline | 20000 |  |  |  | 10000 | 10000
1.3.3 | Design Build Out | 150000 |  |  |  |  | 75000 | 75000
1.3.4 | Procure Critical Components | 5000000 |  |  | 5000000
1.3.5 | Procure Contracted Services | 2750000 |  |  | 1500000 | 250000 | 1000000
1.3.6 | Installation Phase | 600000 |  |  |  | 200000 | 200000 | 200000
1.3.7 | Testing Phase | 150000 | [5 empty] | 50000 | 50000 | 50000
1.3.8 | User Training | 100000 | [7 empty] | 100000
1.3.9 | Milestone: Go Live! | 10000 | [7 empty] | 10000
1.4.1 | Project Management | 10000 | [7 empty] | 5000 | 5000
1.4.2 | Project Status Meetings | 25000 | [8 empty] | 25000
1.4.3 | Risk Management | 100000 | [8 empty] | 50000 | 50000
1.4.4 | Update Project Management Plan | 75000 | [9 empty] | 75000
1.5.1 | Audit Procurement | 300000 | [9 empty] | 150000 | 150000
1.5.2 | Document Lessons Learned | 150000 | [10 empty] | 65000 | 85000
1.5.3 | Update Files/Records | 100000 | [10 empty] | 50000 | 50000
1.5.4 | Gain Formal Acceptance | 10000 | [11 empty] | 10000
1.5.5 | Archive Files/Documents | 75000 | [11 empty] | 75000
| Total Budgeted Cost | 9845000 | 22000 | 42000 | 6585000 | 531000 | 1285000 | 325000 | 50000 | 165000 | 80000 | 275000 | 265000 | 220000
|  | Cumulative Planned Value (PV) | 22000 | 64000 | 6649000 | 7180000 | 8465000 | 8790000 | 8840000 | 9005000 | 9085000 | 9360000 | 9625000 | 9845000
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 22710 | 64603 | 6667924 | 7224473 | 8574748 | 8900631 | 8947152 | 9196232 | 9273079 | 9519061 | 9775521 | 9988720 | ← Enter the Actual Costs as calculated from the AC worksheet.
|  | Cumulative Earned Value (EV) | 18750 | 100250 | 5836500 | 6996000 | 8545000 | 8762500 | 8845000 | 9005000 | 8965000 | 9260000 | 9335000 | 9845000 | ← Enter the Earned Value as calculated from the EV worksheet.
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | -3960 | 35647 | -831424 | -228473 | -29748 | -138131 | -102152 | -191232 | -308079 | -259061 | -440521 | -143720
|  | Schedule Variance (SV = EV - PV) | -3250 | 36250 | -812500 | -184000 | 80000 | -27500 | 5000 | 0 | -120000 | -100000 | -290000 | 0
|  | Cost Performance Index (CPI = EV/AC) | 0.82563 | 1.5518 | 0.87531 | 0.96838 | 0.99653 | 0.98448 | 0.98858 | 0.97921 | 0.96678 | 0.97279 | 0.95494 | 0.98561
|  | Schedule Performance Index (SPI = EV/PV) | 0.85227 | 1.5664 | 0.8778 | 0.97437 | 1.0095 | 0.99687 | 1.0006 | 1 | 0.98679 | 0.98932 | 0.96987 | 1
|  | Estimated Cost at Completion (EAC) | 11924264 | 6344304.5885 | 11247444.8351 | 10166514.6777 | 9879273.7343 | 10000195.4003 | 9958701.1238 | 10054070.4098 | 10183319.8834 | 10120427.1647 | 10309588.0284 | 9988720
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP). | [14 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [14 empty] | © 2012-2021 Vertex42 LLC
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1.1 | Evaluation & Recommendations | 5000 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.2 | Develop Project Charter | 35000 | 35% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.3 | Deliverable: Submit Project Charter | 5000 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.4 | Project Sponsor Reviews Project Charter | 3000 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.5 | Project Charter Signed/Approved | 1000 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.2.1 | Create Preliminary Scope Statement | 10000 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.2.2 | Determine Project Team | 55000 |  | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.2.3 | Project Team Kickoff Meeting | 10000 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.2.4 | Develop Project Plan | 50000 |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.2.5 | Submit Project Plan | 20000 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.2.6 | Milestone: Project Plan Approval | 1000 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.3.1 | Project Kickoff Meeting | 25000 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.3.2 | Confirm Deliverables and Deadline | 20000 |  |  |  | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.3.3 | Design Build Out | 150000 |  |  |  |  | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.3.4 | Procure Critical Components | 5000000 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.3.5 | Procure Contracted Services | 2750000 |  |  | 25% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.3.6 | Installation Phase | 600000 |  |  |  | 20% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.3.7 | Testing Phase | 150000 | [5 empty] | 15% | 70% | 100% | 100% | 100% | 100% | 100%
1.3.8 | User Training | 100000 | [7 empty] | 100% |  |  |  | 100%
1.3.9 | Milestone: Go Live! | 10000 | [7 empty] | 100% |  |  |  | 100%
1.4.1 | Project Management | 10000 | [7 empty] | 50% | 100% |  |  | 100%
1.4.2 | Project Status Meetings | 25000 | [8 empty] | 100% |  |  | 100%
1.4.3 | Risk Management | 100000 | [8 empty] | 40% | 100% |  | 100%
1.4.4 | Update Project Management Plan | 75000 | [9 empty] | 100% |  | 100%
1.5.1 | Audit Procurement | 300000 | [9 empty] | 65% | 100% | 100%
1.5.2 | Document Lessons Learned | 150000 | [10 empty] | 50% | 100%
1.5.3 | Update Files/Records | 100000 | [10 empty] | 70% | 100%
1.5.4 | Gain Formal Acceptance | 10000 | [11 empty] | 100%
1.5.5 | Archive Files/Documents | 75000 | [11 empty] | 100%
Insert new rows above this one
|  | Cumulative EV | 18750 | 100250 | 5836500 | 6996000 | 8545000 | 8762500 | 8845000 | 9005000 | 8965000 | 9260000 | 9335000 | 9845000

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period. | [14 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [14 empty] | © 2012-2021 Vertex42 LLC
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1.1 | Evaluation & Recommendations |  | Wk 1: 4495
1.1.2 | Develop Project Charter |  | Wk 1: 16014; Wk 2: 20054
1.1.3 | Deliverable: Submit Project Charter |  | Wk 2: 5013
1.1.4 | Project Sponsor Reviews Project Charter |  | Wk 1: 2201; Wk 2: 756
1.1.5 | Project Charter Signed/Approved |  | Wk 2: 1333
1.2.1 | Create Preliminary Scope Statement |  | Wk 2: 10052
1.2.2 | Determine Project Team |  | Wk 2: 4685; Wk 3: 51425
1.2.3 | Project Team Kickoff Meeting |  | Wk 3: 11112
1.2.4 | Develop Project Plan |  | Wk 3: 25005; Wk 4: 25007
1.2.5 | Submit Project Plan |  | Wk 4: 19854
1.2.6 | Milestone: Project Plan Approval |  | Wk 4: 1420
1.3.1 | Project Kickoff Meeting |  | Wk 4: 23125
1.3.2 | Confirm Deliverables and Deadline |  | Wk 4: 11021; Wk 5: 98545
1.3.3 | Design Build Out |  | Wk 5: 77480; Wk 6: 74335
1.3.4 | Procure Critical Components |  | Wk 3: 4965125
1.3.5 | Procure Contracted Services |  | Wk 3: 1550654; Wk 4: 274112; Wk 5: 985465
1.3.6 | Installation Phase |  | Wk 4: 202010; Wk 5: 188785; Wk 6: 200546
1.3.7 | Testing Phase |  | Wk 6: 51002; Wk 7: 46521; Wk 8: 48556
1.3.8 | User Training |  | Wk 8: 96887
1.3.9 | Milestone: Go Live! |  | Wk 8: 99584
1.4.1 | Project Management |  | Wk 8: 4053; Wk 9: 5125
1.4.2 | Project Status Meetings |  | Wk 9: 25220
1.4.3 | Risk Management |  | Wk 9: 46502; Wk 10: 48552
1.4.4 | Update Project Management Plan |  | Wk 10: 62005
1.5.1 | Audit Procurement |  | Wk 10: 135425; Wk 11: 142551
1.5.2 | Document Lessons Learned |  | Wk 11: 65025; Wk 12: 84965
1.5.3 | Update Files/Records |  | Wk 11: 48884; Wk 12: 46512
1.5.4 | Gain Formal Acceptance |  | Wk 12: 8522
1.5.5 | Archive Files/Documents |  | Wk 12: 73200
Insert new rows above this one
|  | Total Actual Cost | 22710 | 41893 | 6603321 | 556549 | 1350275 | 325883 | 46521 | 249080 | 76847 | 245982 | 256460 | 213199
|  | Cumulative Actual Cost (AC) | 22710 | 64603 | 6667924 | 7224473 | 8574748 | 8900631 | 8947152 | 9196232 | 9273079 | 9519061 | 9775521 | 9988720

## ©
Earned Value Management (EVM) Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/earned-value-management.html
© 2013-2021 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet