## Lessons Learned Template
Lessons Learned
Today's Date: | May/03/2025
Project Name: | ACC BCC Expansion Project
Project Manager: | Cody Cusey
WIN or ISSUE | Describe What Happened | What Was the Impact? | How Does This Change Future Projects? | Action Items
WIN | Successfully implemented fully operational production facility. | This led to improved efficiency and doubled production capacity for BCC. | In future projects, ensure current plant can operate with little maintanence prior to project start. | 1. Document the automated deployment process for future reference. 2. Conduct training sessions for team members on the new deployment process.
ISSUE | Engineer left the project unexpectedly, causing a shortage in available labor hours. | Project timeline was unaffected, but resources usage had to be reallocated, causing issues with currect production. | In future projects, implement knowledge transfer and maintain detailed documentation to handle risks associated with team turnover. | 1. Conduct a knowledge transfer session with remaining team members. 2. Review project documentation to ensure it is up-to-date and comprehensive.
ISSUE | Centrifuge supplier experienced natural disaster and had to forfit bid. | Had to source components in an expidited fashion causing costs to increase | In future projects, conduct thorough vetting process across all potential suppliers. Have backup supplier on retainer. | 1. Enhance supply chain robustness by performing more thorough RFP and RFQ processes.
WIN | Successfully conducted user acceptance testing (UAT), resulting in positive feedback and minimal defects. | UAT process validated platform functionality and ensured alignment with user expectations, leading to increased confidence in readiness for deployment. | In future projects, prioritize thorough UAT to ensure product quality and alignment with user needs, mitigating risks of post-deployment issues. | 1. Document UAT procedures and best practices for future reference. 2. Incorporate UAT feedback loop into project planning and execution.
WIN | Successfully integrated new Delta V process controllers into existing framework | New production plant can have cost centers quantified, and operators have full control over plant components | New build outs should incorporate the Delta V controllers and supporting systems into the Capital Expenditure Request. | 1. Document the integration process for future reference.